## Sheet1
SYD2 Lane Cove Complaint Register
Date of Compliant | Compaint Details | Responsible person who Dealt with the Compliant | Action Taken
2023-03-01 | Objection raised during Mod 3 Submission. Complaint related noise levels outside of the industrial park, specifically Magdala Park | Town Planner | Operational noise monitoring undertaken with report issued via MOD submission demonstrating compliance to noise limits.
2025-01-24 | Owner of Nicky's Kids Town came to site at 7:30 am as 3 cars were parked in their carpark.They communicated that the cars could stay there for the day, but wanted to make a note that they can not be there moving forward, as it stops parents from doing safe morning drop off | AWE - Project Manager | Photos of the cars were taken and sent to the site supervisors for each company. They were told to move the cars in the next hour, or the wheels would be clamped. All 3 cars were moved within the hour.
2025-01-24 | Depatment of Planning contacted AirTrunk about a complaint related to potential noise exceedance associated with the site. | AirTrunk - Project Manager | Response issued to Department of Planning in Feb 2025 providing compliance documentation for the site and confirming methodology for noise verification and timing associated with noise verification testing.